## Slide 1: Kingston and Richmond’s Children and Young People’s Mental Health Review Programme Update
John Atherton
Director of Mental Health Transformation
South West London Integrated Care Board
March 2025

## Slide 2: Contents
Background and context
Review recommendations
Programme Structure and governance
Approach and timeline
Programme risks and mitigation

## Slide 3: Background and Context
SWL ICB commissioned an independent review of children and young people's (CYP) mental health (MH) services in Kingston and Richmond. The review aimed to assess the effectiveness of the current service configuration in meeting the needs of CYP and their families while also examining reported variations in access, waiting times, and service user experiences compared to other South West London boroughs.
The review made five recommendations focused on strategic leadership, ownership, accountability and clinical pathways. These recommendations are guiding the ICB’s work with system partners and providers to improve service provision.
Kingston and Richmond Place Team launched a dedicated transformation programme and is in the process of implementing the recommendations to develop a new service model.
A Transformation Steering Group was formed in November 2024 to lead the design and implementation of new clinical pathways, aligned with the iThrive framework.

## Slide 4: Review Recommendations
Develop a new core delivery model moving away from the 2-provider model
Agree a place-based vision for the model of care informed by the iThrive framework
Implementation of the revised model of care
Implement a trusted and flexible model of care
Realign the neurodevelopmental pathway with the new model of care

## Slide 5: Programme Structure
Objectives 1 & 2: Identify a strategic partner (Commissioning Lead) Implement a lead / single provider model (Tiers 2 & 3) Recommendation 1 | Objective 3: Co-develop a new vision for the model of care (iThrive) Recommendation 2 | Objective 4: Re-align the neurodevelopmental pathway with model of care Recommendation 5 | Objective 5: Implement a trusted and flexible model of care Recommendation 3, 4
Roles and Responsibilities |  |  | 
SRO: John Atherton Programme Director: Omid Gilanshah Project Management: Sharron Nelson, Arlene Thompson-Dickson, Fiona Murray | SRO: Dr Stavroula Lees Programme Director: Omid Gilanshah (interim cover) Project Management: Arlene Thompson-Dickson, Fiona Murray | SRO: Denise Madden Programme Director: Omid Gilanshah (interim cover) Project Management: Arlene Thompson-Dickson, Fiona Murray | SRO: Denise Madden Programme Director: Omid Gilanshah (interim cover) Project Management: TBC
Delivery Status |  |  | 
On Track – All partners are engaged and defining services to transfer and contractual route identified. | On Track – The iThrive sub-group is reviewing legacy approaches and defining key benefits to inform vision. | Initiated – Requires scoping and alignment to development of a new vision for the model of care (iThrive). | Initiated – Requires scoping and alignment to development of a new vision for the model of care (iThrive) and realignment of the neurodevelopmental pathway.

## Slide 6
Programme governance
Children & Young People’s Mental Health Review Implementation Steering Group
Co-Chairs: John Atherton & Denise Madden
Kingston & Richmond Integrated Mental Health Committee
Kingston & Richmond Place Committees
CAMHS Review Implementation Delivery Group
Chair: Omid Gilanshah
iThrive Design Group
Chair: Dr Stavroula Lees

## Slide 7: Approach & Timeline
Challenges Identified
Identify Current State Understanding of Capacity and Demands
Engage with Stakeholders
Define Future State & Model and Benefits
Mobilisation & Implement Model of Care
Step 1
Step 2
Step 3
The independent review sets out many of the known challenges
Step 4
We are here
Objectives 3 & 4
(recommendations 2, 5)
Objective 5
(recommendations 3, 4)
Objectives 1 & 2
(recommendation 1, 2)
Q4 24/25 & Q1 25/26
From Q2 25/26
Q3 24/25
Q2 24/25
Q1 24/25
Note: Working with partners to agree timeframes

## Slide 8: Programme Risks and Mitigations
No | Risk | Mitigation Strategy
1 | Resistance to change from providers and stakeholders | Establish a strong engagement plan involving system partners, clinicians, and service users. Use co-production approaches to ensure buy-in from all stakeholders.
2 | Workforce capacity | Work with providers to develop a workforce strategy, including training, upskilling, and retention initiatives. Explore flexible staffing models and alternative roles to support service delivery.
3 | Financial and budgetary constraints | Conduct a detailed financial impact assessment and ensure clear funding allocation. Implement phased rollouts to manage costs effectively and secure additional investment if needed.
4 | Integration challenges between Tier 2 and Tier 3 Services | Develop clear governance structures and accountability mechanisms. Implement joint protocols for referrals, escalation, and information sharing.
5 | Disruption to existing services during transition | Ensure robust transition planning, including risk assessments, phased implementation, and effective communication to service users and families.
6 | Variation in service user experience post implementation | Implement standardised clinical pathways and performance monitoring across providers to ensure consistency.
7 | IT and data-sharing barriers | Work with IT teams to enable secure data-sharing agreements and ensure systems interoperability. Use digital solutions to improve data flow and decision-making.
8 | Unrealistic expectations and scope creep | Define clear programme scope and deliverables, managing expectations through transparent communication with stakeholders.